GREENWICH STOW CREEK PARTNERSHIP SCHOOLS	FILE CODE: 7430

POLICY MANUAL

Policy

# Change orders

Contract Change Orders for Capital Projects

Contract change orders for capital projects are governed by the following:

- Change orders may be approved by the board, in an amount up to and including 20 percent of the award amount, which includes the amount encumbered pursuant to N.J.A.C. 6A:26-4.8(c), but for no more than the approved referendum amount for a capital project funded in whole or in part by bond proceeds, when necessitated by one of the following:

- Emergencies consistent with N.J.S.A 18A:18A-7 (emergencies affecting the health or safety of occupants of the school property requires the immediate delivery of goods or the performance of services);

- Unforeseeable physical conditions; or

- Minor modifications to project scope that achieve cost savings, improve service or resolve construction conditions.

- All other change orders including, but not limited to, the following, shall be approved by the Division of Facilities and Transportation, which approval shall be granted only upon a determination by the Division that an extraordinary circumstance exists:

  - Change orders that, in the aggregate, increase the amount of the original award of each individual contract, or of the entire project, by greater than 20 percent, but for no more than the approved referendum, including changes funded by project contingency in N.J.A.C. 6A:26-4.8(c) (an amount equal to no less than five percent of the total costs of construction of a capital project, against which change orders may be approved, but shall not exceed the approved referenda amount if the capital project is funded wholly or in part by bond proceeds).

  - Change orders that eliminate or affect the project scope that was the basis of the Division's determination of the final eligible costs of a school facilities project pursuant to N.J.A.C. 6A:26-3.6; or

  - Change orders that affect the number, size, configuration, location or use of educational spaces.

Authorization of Change Orders

Before the school district or Division may authorize a change order that increases the contract amount, the availability of funds shall be certified by the board secretary, on a form prescribed by the Commissioner, that indicates:

- The original contract amount and funds allocated to each contract in the overall project;

- All payments made to date;

- All change orders approved and pending to date;

- The percentage of the project that is completed, and the percentage of the contract cost remaining; and

- The funds available to complete project, including all change orders that were executed or that are pending.

The board directs the superintendent to report any significant changes in the scope of the project to the public.  The superintendent may elect to make such reports at a regularly scheduled meeting of the board or by other appropriate means.

The board attorney shall be responsible for reviewing all construction contracts to be entered into by the board. In general, all contracts or agreements which require public advertisement for bids shall be awarded to the lowest responsible bidder.  However, the board reserves the right to reject all bids.

Greenwich:

Adopted:	October 2, 2008

NJSBA Review/Update:	August 2022

Readopted:

Stow Creek:

Adopted:	May 19, 2008

NJSBA Review/Update:	August 2022

Readopted:

Key Words

Capital Project, Change Orders,

Legal References: N.J.S.A 18A:18A-7 	Emergency contracts

N.J.A.C. 6A:26-3.6 	Determination of final eligibility costs for nonauthority

facilities projects

N.J.A.C. 6A:26-4.8 	Bidding and awarding of contract for nonauthority capital

projects

Possible

Cross References:	*1330		Use of school facilities

*2224		Nondiscrimination/affirmative action

*3100		Budget planning, preparation, and adoption

*3320		Purchasing procedures

*3326		Payment for goods and services

*3327		Relations with vendors

*4119.21/4219	Conflict of interest

*9270		Conflict of interest

*Indicates policy is included in the Critical Policy Reference Manual.